## Filters
ContractReference | Description | DueDate | Value | ContractItemId | UserName | LineReferenceNumber | AluminiumSystem | Status | Handover to Factory Start | Handover to Factory Complete | Issued for Manufacturing Start | Issued for Manufacturing Complete | Cutting Aluminium Start | Cutting Aluminium Complete | Machining Start | Machining Complete | Assembly Start | Assembly Complete | Glazing Start | Glazing Complete | Quality Control Start | Quality Control Complete | Wrapping and Despatching Start | Wrapping and Despatching Complete | Delivery Start | Delivery Complete | Installation Start | Installation Complete | Snagging Start | Snagging Complete | Cancelled | On Hold/Problem Start | On Hold/Problem Complete
C18071520 | S.G.B. MAINTANANCE GAIL | 2018-08-21 | 6961.1 | 337 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:09
C18071520 | S.G.B. MAINTANANCE GAIL | 2018-08-21 | 6961.1 | 337 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:09
C18071520 | S.G.B. MAINTANANCE GAIL | 2018-08-21 | 0 | 338 |  | Cottg01-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:09
C18071520 | S.G.B. MAINTANANCE GAIL | 2018-08-21 | 6894.95 | 339 |  | Cottg01-D02Dr | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:09
C18071520 | S.G.B. MAINTANANCE GAIL | 2018-08-21 | 0 | 340 |  | Cottg01-D02SL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:09
T19981 | Test19981 | 2018-08-24 | 200 | 326 |  | qw1-1 | win1 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 200 | 327 |  | qw1-2 | win1 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 500.5 | 328 |  | qw2-1 | win2 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 500.5 | 329 |  | qw2-2 | win2 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 500.5 | 330 |  | qw2-3 | win2 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 500.5 | 331 |  | qw2-4 | win2 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 200 | 332 |  | qw5-1 | win5 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 200 | 333 |  | qw5-2 | win5 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 200 | 334 |  | qw5-3 | win5 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 100.1 | 335 |  | qw3 | win3 | Handover to Factory Start | 2019-01-11 08:52
T19981 | Test19981 | 2018-08-24 | 100 | 336 |  | qw4 | win4 | Handover to Factory Start | 2019-01-11 08:52
F1188912 | Fourier-E | 2018-08-30 | 6961.1 | 342 |  | 1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 0 | 343 |  | 2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 6894.95 | 344 |  | 3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 0 | 345 |  | 4 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 5592.22 | 346 |  | 5 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 0 | 347 |  | 6 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:16
F1188912 | Fourier-E | 2018-08-30 | 2723.18 | 348 |  | 7 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:16
Q18081565 | Malvin Mashaba | 2018-08-31 | 3285 | 171 | Alpheus Mjabulise Mziz | D01 | Clip 44 Single Hinged Door | Glazing Start |  | 2018-10-18 13:17 | 2018-09-06 08:24 |  |  |  |  | 2018-10-30 09:34 | 2019-01-08 08:39 | 2019-01-08 08:39 | 2019-01-08 08:39 | 2018-09-13 12:55 |  |  |  |  | 2018-10-19 14:33
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 100 | 377 |  | Cottg01-D02SL-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:15
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 378 |  | Cottg01-D02SL-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 6961.1 | 379 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 380 |  | Cottg01-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 6894.95 | 381 |  | Cottg01-D02Dr | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 5592.22 | 382 |  | Cottg01-D03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 383 |  | Cottg01-W01 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 2723.18 | 384 |  | Cottg01-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 385 |  | Cottg01-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 4360.36 | 386 |  | Cottg01-W03B | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 557.02 | 387 |  | Cottg01-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 536.54 | 388 |  | Cottg01-W05A | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1094.18 | 389 |  | Cottg01-W05B | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1099.07 | 390 |  | Cottg01-W05C | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1037.28 | 391 |  | Cottg02-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 320.57 | 392 |  | Cottg02-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 3112.74 | 393 |  | Cottg02-D02 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 3061.26 | 394 |  | Cottg02-D02ins | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 2725.65 | 395 |  | Cottg02-W01 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 2763.45 | 396 |  | Cottg02-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 8512.66 | 397 |  | Cottg02-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 398 |  | Cottg02-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1436.67 | 399 |  | Cottg02-W05 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 0 | 400 |  | Cottg02-W06 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 3450.81 | 401 |  | Cottg02-W07 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1269.17 | 402 |  | Cottg02-W08 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 1063.9 | 403 |  | Cottg03-D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
Q18081505-1 | BATANI SHAFIN | 2018-09-10 | 453.49 | 404 |  | Cottg03-D02 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 11:14
C201807-01test | test 123 | 2018-10-13 | 3489.21 | 176 |  | AB D1-1 | Door | Handover to Factory Complete | 2018-09-10 12:33 | 2018-10-18 13:17
C201807-01test | test 123 | 2018-10-13 | 3489.21 | 177 | Admin2 | AB D1-2 | Door | Cutting Aluminium Start | 2018-09-10 12:33 | 2018-10-18 13:17 | 2019-01-08 15:41 | 2019-01-09 14:38 | 2019-01-09 14:38
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 2589 | 216 | Charlie Msiza | W01 | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-22 15:53 | 2018-11-27 08:34
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1976 | 217 | Patric Kola | W02A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:34
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1976 | 218 | ShaSha Raulinga | W02B | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-27 07:37 | 2018-12-03 00:15
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 219 | Patric Kola | W03A | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-27 07:38 | 2018-12-03 00:15
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 220 | Patric Kola | W03B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:39
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 221 | Charlie Msiza | W03C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:48
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 222 | Charlie Msiza | W03D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:50
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 223 | Charlie Msiza | W03E | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:51
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1710 | 224 | Steph Ngubeni | W04A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:53
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1710 | 225 | Obed M Tlale | W04B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:54
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1060 | 226 | Obed M Tlale | W05A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:55
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1444 | 227 | Obed M Tlale | W05B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:56
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1060 | 228 | Obed M Tlale | W05 LAM | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:58
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1444 | 229 | ShaSha Raulinga | W05 TSG OBS | CASEMENT 30.5 WINDOW | Handover to Factory Complete |  | 2018-11-27 07:59
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 961 | 230 | ShaSha Raulinga | W06 | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:00
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 231 | ShaSha Raulinga | W07A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:01
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 232 | ShaSha Raulinga | W07B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:02
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 233 | Obed M Tlale | W07C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:04
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 234 | Steph Ngubeni | W07D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:06
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 235 | Steph Ngubeni | W07 TSG OBS A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:07
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 236 | Steph Ngubeni | W07 TSG OBS B | CASEMENT 30.5 WINDOW | Handover to Factory Complete |  | 2018-11-27 08:08
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 237 | Obed M Tlale | W07 TSG OBS C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:09
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 238 | Obed M Tlale | W07 TSG OBS D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:10
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 239 | Obed M Tlale | W07 TSG OBS E | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:11
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 240 | Obed M Tlale | W07 TSG OBS F | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:12
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 241 | Charlie Msiza | W09A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:13
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1274 | 242 | Charlie Msiza | W09B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:13
C3192-test | Test321 | 2018-11-30 | 0 | 349 |  | Cottg01-D02SL-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 350 |  | Cottg01-D02SL-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 6961.1 | 351 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 352 |  | Cottg01-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 6894.95 | 353 |  | Cottg01-D02Dr | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 5592.22 | 354 |  | Cottg01-D03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 355 |  | Cottg01-W01 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 2723.18 | 356 |  | Cottg01-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 357 |  | Cottg01-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 4360.36 | 358 |  | Cottg01-W03B | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 557.02 | 359 |  | Cottg01-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 536.54 | 360 |  | Cottg01-W05A | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1094.18 | 361 |  | Cottg01-W05B | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1099.07 | 362 |  | Cottg01-W05C | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1037.28 | 363 |  | Cottg02-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 320.57 | 364 |  | Cottg02-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 3112.74 | 365 |  | Cottg02-D02 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 3061.26 | 366 |  | Cottg02-D02ins | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 2725.65 | 367 |  | Cottg02-W01 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 2763.45 | 368 |  | Cottg02-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 8512.66 | 369 |  | Cottg02-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 370 |  | Cottg02-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1436.67 | 371 |  | Cottg02-W05 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 0 | 372 | Admin2 | Cottg02-W06 | 1000 Sliding Window | Machining Complete | 2019-01-11 09:37 | 2019-01-11 13:24 | 2019-01-11 13:24 | 2019-01-11 13:26 | 2019-01-11 13:27 | 2019-01-11 13:27 | 2019-01-11 13:27 | 2019-01-11 15:19
C3192-test | Test321 | 2018-11-30 | 3450.81 | 373 |  | Cottg02-W07 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1269.17 | 374 |  | Cottg02-W08 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 1063.9 | 375 |  | Cottg03-D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
C3192-test | Test321 | 2018-11-30 | 453.49 | 376 |  | Cottg03-D02 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 09:37
Q18091932 | Nick Artisans | 2018-12-05 | 10898.59 | 263 |  | D01 | WPalaceM | Assembly Start | 2018-11-30 09:15 | 2018-11-30 09:22 | [6 empty] | 2018-11-30 09:22
Q18091932 | Nick Artisans | 2018-12-05 | 8500.09 | 442 |  | D02-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 8500.09 | 443 |  | D02-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 8500.09 | 444 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 7893.24 | 445 |  | D03-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 7893.24 | 446 |  | D03-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 6767.26 | 447 |  | D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 6322.78 | 448 |  | D01-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18091932 | Nick Artisans | 2018-12-05 | 6322.78 | 449 |  | D01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:57
Q18082301B | DuPlessis - Extras | 2018-12-06 | 444.4 | 207 | Lucky Nekhudzhiga | W4 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [18 empty] | 2018-09-12 08:46
Q18082301B | DuPlessis - Extras | 2018-12-06 | 555.5 | 208 |  | WS-2 | window | Cancelled |  | 2018-10-18 13:17 | [17 empty] | 2018-09-12 08:48 |  |  | 2018-10-19 14:31
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 160 |  | WA-1 | Crealco Swift 30.5 Window -1 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [7 empty] | 2018-09-10 15:12 |  | 2018-08-13 22:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 161 |  | WA-2 | Crealco Swift 30.5 Window -2 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [9 empty] | 2018-08-27 11:48 | 2018-08-27 11:48
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 162 | Reginald Nemalili | WA-3 | Crealco Swift 30.5 Window -3 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 163 | Admin2 | WB-1 | Crealco Swift 30.5 Window -1 | Assembly Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | 2019-01-08 11:00 | 2019-01-08 15:41 | 2019-01-08 15:42 | 2019-01-08 15:42 | 2019-01-08 15:42 | 2019-01-09 08:14 | 2019-01-09 08:15 | 2019-01-10 14:12
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 164 |  | WB-2 | Crealco Swift 30.5 Window -2 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [7 empty] | 2018-08-15 08:31
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 165 |  | WB-3 | Crealco Swift 30.5 Window -3 | Glazing Start | 2018-08-13 20:53 | 2018-10-18 13:17 | [8 empty] | 2018-12-07 10:14
Q18082301B | DuPlessis - Extras | 2018-12-06 | 742 | 166 |  | WC | Crealco Swift 30.5 Window | Cutting Aluminium Start | 2018-08-13 20:53 | 2018-10-18 13:17 |  |  | 2018-10-19 14:27
Q18082301B | DuPlessis - Extras | 2018-12-06 | 789 | 167 | Werner Rohrs | WG-2 | Crealco Swift 30.5 window | Wrapping and Despatching Complete | 2018-08-15 09:24 | 2018-10-18 13:17 | 2018-12-05 09:52 | 2018-12-06 12:06 | 2018-12-06 14:20 | 2018-09-13 12:52 | 2018-12-06 14:43 | 2018-12-06 14:43 | 2018-12-06 15:05 | 2019-01-07 13:29 | 2019-01-07 13:29 | 2019-01-14 08:17 | 2019-01-14 08:17 | 2019-01-14 08:17 | 2019-01-14 08:17 | 2019-01-14 08:17
Q18100751 | Alves | 2018-12-07 | 6515 | 265 | Admin2 | W30 | Side hung | Snagging Complete | [5 empty] | 2018-11-30 11:04 | 2018-12-03 00:16 | 2018-12-03 09:12 | 2018-12-03 21:05 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-04 12:56 | 2018-12-05 08:58 | 2018-12-06 11:10 | 2018-12-06 12:14 | 2018-12-06 12:38 | 2019-01-14 08:08 | 2019-01-14 08:09 | 2019-01-14 14:14 | 2019-01-14 14:16
Q18100751 | Alves | 2018-12-07 | 5131 | 266 | Werner Rohrs | W27 | Side hung | Issued for Manufacturing Start |  |  | 2019-01-14 09:04 |  |  | 2018-11-30 11:12 | 2018-12-03 09:25 | 2018-12-06 12:38
Don | Office | 2018-12-11 | 2689 | 264 | Reymond Moshoeu | D01 | Prima PD | Machining Complete |  |  |  |  | 2018-11-30 10:46 | 2018-11-30 10:56 | 2018-11-30 11:52 | 2018-11-30 13:18
Q18060734 | Peace Msinde | 2018-12-12 | 1000 | 277 |  | D01B | WClip44 | Assembly Complete | [9 empty] | 2018-12-05 15:16 | [12 empty] | 2018-12-06 07:30
Q18060734 | Peace Msinde | 2018-12-12 | 1000 | 278 | Steph Ngubeni | W01 | Palace | Assembly Complete | [9 empty] | 2018-12-06 07:17
Q18060734 | Peace Msinde | 2018-12-12 | 1000 | 279 | Zulu S Mbongeleni | W02 | Palace | Assembly Complete | [9 empty] | 2018-12-06 07:19
Q18060734 | Peace Msinde | 2018-12-12 | 3000 | 280 | Daniel Kanyane (Daniels) | SD02 | Vista | Assembly Complete | [9 empty] | 2018-12-06 07:20
Q18060734 | Peace Msinde | 2018-12-12 | 3500 | 281 | Patric Kola | SD03 | Vista | Assembly Complete | [9 empty] | 2018-12-06 07:21
Q18060734 | Peace Msinde | 2018-12-12 | 2500 | 282 | Francois Burger | SD04 | Dbl Hinged Door | Assembly Complete | [7 empty] | 2018-12-06 07:22 | 2018-12-06 08:07 | 2018-12-06 08:08
Q18060734 | Peace Msinde | 2018-12-12 | 2500 | 283 | Francois Burger | SD05 | Dbl Hinged Door | Machining Complete | [7 empty] | 2018-12-06 07:23
Q18060734 | Peace Msinde | 2018-12-12 | 3850 | 284 | Francois Burger | SD07 | Dbl Hinged Door | Assembly Complete | [7 empty] | 2018-12-06 07:25 | 2018-12-06 08:03 | 2018-12-06 08:04
Q18060734 | Peace Msinde | 2018-12-12 | 1800 | 285 | Phophi Raulinga | Man. Office Frm | Window | Machining Complete | [6 empty] | 2018-12-06 11:08 | 2018-12-06 11:08 |  |  | 2018-12-06 07:27 | 2018-12-06 11:07
Q18060734 | Peace Msinde | 2018-12-12 | 1000 | 286 | Phophi Raulinga | Store room | WClip44 | Glazing Start | [10 empty] | 2018-12-06 07:28
Q18060734 | Peace Msinde | 2018-12-12 | 8992 | 267 |  | D01A | WClip44 | Assembly Complete | [8 empty] | 2018-12-04 14:41 | 2018-12-04 15:34
Q18060734 | Peace Msinde | 2018-12-12 | 7962 | 268 | Daniel Kanyane (Daniels) | SD06 | WClip44 | Assembly Start | [8 empty] | 2018-12-04 14:41
Q18060734 | Peace Msinde | 2018-12-12 | 9955 | 271 | Patric Kola | D02 | WVista | Assembly Complete | [8 empty] | 2018-12-04 15:11 | 2018-12-06 07:49
C201807-01test | Test q1 | 2018-12-21 | 400.5 | 172 | Charlie Msiza | A100 | Window 100 | Installation Start | 2018-09-06 09:25 | 2018-10-18 13:17 | [16 empty] | 2018-10-19 14:13
C201807-01test | Test q1 | 2018-12-21 | 123.63 | 175 | Patric Kola | AB D1 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 |  |  |  |  | 2018-09-10 12:28
C201807-01test | Test q1 | 2018-12-21 | 1290 | 169 | Charlie Msiza | A18 | Window 2100 | Cutting Aluminium Start | 2018-08-23 21:06 | 2018-10-18 13:17 |  |  | 2018-10-19 09:13
C201807-01test | Test q1 | 2018-12-21 | 1290 | 170 | Alpheus Mjabulise Mziz | A19 | Window 2101 | Issued for Manufacturing Start | 2019-01-07 14:15 | 2019-01-07 14:16 | 2019-01-07 13:30 | 2019-01-07 13:30
C201807-01test | Test q1 | 2018-12-21 | 500 | 132 | Admin2 | A2-1 | Win 29-1 | Assembly Start | 2019-01-07 14:37 | 2019-01-07 14:43 | 2019-01-07 14:44 | 2018-12-06 13:54 | 2019-01-07 14:46 | 2019-01-07 14:46 | 2019-01-07 14:46 | 2019-01-07 14:47 | 2019-01-07 14:47 | 2019-01-07 14:47 | 2019-01-08 08:10 | 2019-01-08 08:11 | 2019-01-08 08:11 | 2019-01-08 08:11 | 2019-01-08 10:59 | 2018-12-06 13:23 | 2018-12-06 13:29 | 2019-01-07 13:36 | 2019-01-07 14:03 | 2018-12-06 13:29 | 2019-01-09 15:15 | 2019-01-09 15:16 | 2018-12-06 13:45
C201807-01test | Test q1 | 2018-12-21 | 500 | 133 | Admin2 | A2-2 | Win 29-2 | Snagging Complete | 2018-08-13 09:03 | 2018-10-18 13:17 | [8 empty] | 2018-10-30 12:29 | 2018-12-06 13:25 | 2018-09-14 13:31 | 2018-12-06 13:44 | 2018-12-06 15:05 | 2019-01-07 13:06 | 2019-01-07 13:17 | 2019-01-07 13:29 | 2019-01-07 13:36 | 2019-01-08 10:59 | 2019-01-08 15:29 | 2019-01-09 08:11
C201807-01test | Test q1 | 2018-12-21 | 500 | 134 | Alpheus Mjabulise Mziz | A2-3 | Win 29-3 | Issued for Manufacturing Start | 2018-08-13 09:03 | 2018-09-17 20:50 | 2019-01-14 13:38 | [15 empty] | 2018-10-19 09:05 | 2018-12-07 11:00 | 2019-01-08 15:33 | 2019-01-10 08:32
C201807-01test | Test q1 | 2018-12-21 | 500 | 135 | Admin2 | A2-4 | Win 29-4 | Installation Start | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-08-13 09:13 | 2018-09-17 20:50 | [6 empty] | 2018-12-07 09:48 | 2019-01-07 13:08 | 2019-01-07 14:42 | 2019-01-07 14:43 | 2019-01-08 15:31 | 2019-01-08 15:32 | 2019-01-10 09:16 | 2019-01-10 14:11 | 2019-01-10 14:11
C201807-01test | Test q1 | 2018-12-21 | 500 | 136 | Alpheus Mjabulise Mziz | A2-5 | Win 29-5 | Installation Start | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-08-13 09:12 | 2018-08-13 09:27 | 2018-08-13 09:13 | [5 empty] | 2018-12-07 09:49 | 2019-01-07 13:08 | 2019-01-07 14:43 | 2019-01-08 15:27 | 2019-01-08 15:29 | 2019-01-08 15:31 | 2019-01-14 11:59 | 2019-01-14 13:14 | 2019-01-14 13:16
C201807-01test | Test q1 | 2018-12-21 | 230 | 137 |  | B1-1 | Dr 10-1 | Delivery Complete | 2018-08-13 09:03 | 2018-10-18 13:17 | [8 empty] | 2019-01-14 11:59: 2018-12-07 09:54; 2019-01-14 13:14: 2019-01-08 15:31
C201807-01test | Test q1 | 2018-12-21 | 230 | 138 | Admin2 | B1-2 | Dr 10-2 | Installation Start | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-12-06 13:27 | 2018-12-07 09:54 | [6 empty] | 2019-01-14 11:59: 2018-12-07 10:05; 2019-01-14 13:14: 2019-01-11 11:00; 2019-01-14 13:16: 2019-01-11 12:23
C201807-01test | Test q1 | 2018-12-21 | 200 | 139 | Alpheus Mjabulise Mziz | A1 | Win 10 | Issued for Manufacturing Start | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-09-06 12:16 |  |  |  | 2018-09-06 12:16 | 2018-09-06 12:26 |  |  | 2019-01-14 11:59: 2018-09-06 12:26; 2019-01-14 13:14: 2018-09-06 12:30
C201807-01test | Test q1 | 2018-12-21 | 1125 | 140 | Admin2 | W01-1 | Cas30.5 | Assembly Complete | 2018-08-13 20:05 | 2018-10-18 13:17 | 2019-01-08 15:26 | 2019-01-08 15:28 | 2019-01-11 15:14 | 2019-01-11 15:14 | 2019-01-11 15:19 | 2019-01-11 15:19 | 2019-01-11 15:19 | 2019-01-14 11:13
Q18111303B | Koning | 2018-12-21 | 1945 | 246 |  | W01-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1945 | 247 |  | W01-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1802 | 248 |  | W05-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1802 | 249 |  | W05-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1676 | 250 |  | W06-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1676 | 251 |  | W06-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1500 | 252 |  | W07-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1500 | 253 |  | W07-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1962 | 254 |  | W08-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1962 | 255 |  | W08-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 2879 | 256 |  | W09-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 2879 | 257 |  | W09-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1298 | 258 |  | W02 | Swift 30.5 | Handover to Factory Complete | 2018-11-30 08:53 | 2018-11-30 10:57
Q18111303B | Koning | 2018-12-21 | 1082 | 259 |  | W03 | Swift 30.5 | Handover to Factory Complete | 2018-11-30 08:53 | 2018-12-03 00:23
Q18111303B | Koning | 2018-12-21 | 438 | 260 |  | W04 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 605 | 261 |  | W10 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 829 | 262 |  | W11 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
ab-11 | Ab | 2019-01-17 | 8500.09 | 466 |  | D02-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:38
ab-11 | Ab | 2019-01-17 | 8500.09 | 467 |  | D02-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:38
ab-11 | Ab | 2019-01-17 | 8500.09 | 468 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:38
ab-11 | Ab | 2019-01-17 | 7893.24 | 469 |  | D03-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:38
ab-11 | Ab | 2019-01-17 | 7893.24 | 470 | Alpheus Mjabulise Mziz | D03-2 | Clip 44 Shop Front | Cutting Aluminium Start | 2019-01-14 09:38 | 2019-01-14 11:55 | 2019-01-14 12:28 | 2019-01-14 13:17 | 2019-01-14 13:27
ab-11 | Ab | 2019-01-17 | 6767.26 | 471 | Alpheus Mjabulise Mziz | D01 | Clip 44 Shop Front | Handover to Factory Complete | 2019-01-14 14:12 | 2019-01-14 11:15 | 2019-01-14 12:24 | 2019-01-14 12:30 | 2019-01-14 12:30 | 2019-01-14 12:35 | 2019-01-14 12:35 | 2019-01-14 13:08 | 2019-01-14 13:09 | 2019-01-14 13:14 | 2019-01-14 13:14 | 2019-01-14 13:17 | 2019-01-14 13:17 | 2019-01-14 13:20 | 2019-01-14 13:21 | 2019-01-14 13:40 | 2019-01-14 13:40 | 2019-01-14 13:50 |  |  |  |  | 2019-01-14 11:31 | 2019-01-14 14:07 | 2019-01-14 14:07
ab-11 | Ab | 2019-01-17 | 6322.78 | 472 | Alpheus Mjabulise Mziz | D01-1 | Clip 44 Shop Front | Cutting Aluminium Start | 2019-01-14 09:38 | 2019-01-14 11:31 | 2019-01-14 11:31 | 2019-01-14 13:09 | 2019-01-14 13:10
ab-11 | Ab | 2019-01-17 | 6322.78 | 473 | Alpheus Mjabulise Mziz | D01-2 | Clip 44 Shop Front | Cutting Aluminium Start | 2019-01-14 09:38 | 2019-01-14 11:57 | 2019-01-14 12:26 | 2019-01-14 12:33 | 2019-01-14 12:33
FE-100 | FE | 2019-01-18 | 8500.09 | 457 |  | D02-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 8500.09 | 458 |  | D02-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 8500.09 | 459 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 7893.24 | 460 |  | D03-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 7893.24 | 461 |  | D03-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 6767.26 | 462 |  | D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 6322.78 | 463 |  | D01-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
FE-100 | FE | 2019-01-18 | 6322.78 | 464 |  | D01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:30
T19981 | Fourier Approach | 2019-01-24 | 150.5 | 275 | Cynthia Ngcobo | W0119 | Window | Handover to Factory Start | 2018-12-05 08:45
T19981 | Fourier Approach | 2019-01-24 | 200.3 | 276 | Francois Burger | D1441 | Door | Handover to Factory Complete | 2018-12-05 08:51 | 2019-01-11 15:06
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 141 | Reginald Nemalili | W11-1 | Cas30.5-1 | Snagging Complete | 2018-08-13 20:29 | 2018-09-14 12:43 | 2018-10-19 09:28 | 2018-10-19 14:14 | 2018-11-22 11:38 | 2018-11-22 11:38 | 2018-09-14 13:02 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-21 14:11 | 2018-11-22 11:40 | 2018-09-13 00:02 | 2018-10-30 12:25 | 2018-08-13 20:40 | 2018-08-27 11:55 | 2018-09-06 12:39 | 2018-11-22 11:42 | 2018-11-22 11:43 | 2018-11-22 11:43 | 2018-09-13 13:08 | 2018-11-22 11:37 | 2018-09-14 12:34
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 142 |  | W11-2 | Cas30.5-2 | Quality Control Complete | 2018-08-13 20:29 | 2018-10-30 09:24 | 2018-11-21 14:29 |  | 2018-09-14 12:44 |  | 2018-11-21 14:29 | 2018-08-29 19:33 | 2018-11-21 14:29 | 2018-09-12 16:00 | 2018-12-05 13:12 | 2018-10-19 09:27 | 2018-11-21 14:29 | 2018-12-07 10:20 | 2018-11-21 14:30 | 2018-11-26 10:44 | 2018-10-30 12:26 | 2018-10-30 13:04 | 2018-11-21 14:29 |  |  |  | 2018-09-13 13:08
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 143 |  | W11-3 | Cas30.5-3 | Installation Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [8 empty] | 2018-12-07 09:49: 2018-10-18 13:22; 2019-01-07 13:08: 2018-10-30 12:44; 2019-01-14 11:59: 2018-09-13 13:09; 2019-01-14 13:14: 2018-11-28 11:00; 2019-01-14 13:16: 2018-12-06 13:45 | 2018-09-13 00:03
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 144 |  | W11-4 | Cas30.5-4 | Wrapping and Despatching Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [6 empty] | 2018-09-13 12:53 | 2018-10-18 13:12 | 2019-01-08 15:29: 2018-11-26 11:31; 2019-01-14 11:59: 2018-08-13 20:41; 2019-01-14 13:14: 2018-09-06 08:24 |  |  |  | 2018-11-22 13:26
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 145 | Reginald Nemalili | W11-5 | Cas30.5-5 | Delivery Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [5 empty] | 2018-08-13 21:01 | 2018-08-13 21:16 | 2018-08-13 21:18 |  |  | 2018-10-19 08:59 | 2018-11-28 10:54 | 2018-12-03 15:03 | 2018-12-03 15:04 | 2018-12-03 21:04 | 2018-12-07 10:01
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 146 |  | W01 | Cas30.5 | Snagging Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [10 empty] | 2018-11-28 10:54: 2018-09-12 22:57 |  |  | 2018-11-21 14:32 | 2018-11-29 15:04
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 147 |  | W02 | Cas30.5 | Machining Complete | 2018-08-13 20:29 | 2018-10-18 13:17 |  |  | 2018-11-21 14:40 | 2018-11-30 10:55 | 2018-12-06 13:44 | 2018-12-06 14:21 | 2018-10-30 12:17 | 2018-11-21 14:30 |  |  | 2018-10-19 08:59: 2018-08-29 19:36
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 148 | Alpheus Mjabulise Mziz | W03 | Cas30.5 | Issued for Manufacturing Start | 2018-08-13 20:29 | 2018-08-13 21:13 | 2019-01-14 12:36 | [9 empty] | 2018-12-03 15:04: 2018-09-12 16:01
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 149 | Werner Rohrs | W04 | Cas30.5 | Quality Control Complete | 2018-08-13 20:29 | 2018-08-13 21:13 | [8 empty] | 2018-11-21 14:41 | 2018-11-21 14:42 | 2019-01-14 09:08 | 2019-01-14 11:57 |  |  | 2018-11-26 11:18 | 2018-12-03 21:04
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 150 |  | W05 | Cas30.5 | Snagging Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [8 empty] | 2018-08-27 11:49 | 2018-08-27 11:49 | [8 empty] | 2018-10-19 09:00 | 2019-01-14 09:03
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 151 |  | W06 | Cas30.5 | Delivery Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [10 empty] | 2018-12-03 21:04: 2018-10-19 14:20
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 152 |  | W07 | Cas30.5 | Issued for Manufacturing Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | 2018-11-29 15:05 | 2018-11-29 15:05
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 153 |  | W08 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17 |  | 2018-09-10 15:13
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 154 |  | W09 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 155 |  | W10 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 156 |  | W12 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2019-01-24 | 1400 | 157 |  | W13 | Cas30.5 | Issued for Manufacturing Start | 2018-08-13 20:29 | 2018-10-18 13:17 | 2018-09-13 12:55 | [19 empty] | 2018-11-29 15:06
Q18082501 | DuPlessis | 2019-01-24 | 5000 | 158 | Werner Rohrs | SFD01 | Vistafold | Glazing Start | 2018-08-13 20:29 | 2018-10-18 13:17 |  |  |  |  | 2018-09-13 00:04 |  | 2019-01-14 09:04 | 2019-01-14 09:05 | 2019-01-14 10:29 |  | 2018-12-03 21:04: 2019-01-14 09:05; 2018-12-07 10:01: 2019-01-14 09:38
Q18082501 | DuPlessis | 2019-01-24 | 7000 | 159 | Werner Rohrs | SFD02 | Vistafold | Assembly Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [6 empty] | 2019-01-14 09:37 |  |  |  | 2018-12-03 21:04: 2018-08-13 20:42 | 2019-01-14 09:02 | 2019-01-14 09:04
T19981 | Fourier Approach | 2019-01-24 | 2213.6 | 180 |  | AB D1-1 | W1 | Handover to Factory Complete | 2018-09-10 13:05 | 2018-10-18 13:17
T19981 | Fourier Approach | 2019-01-24 | 2213.6 | 181 |  | AB D1-2 | W1 | Issued for Manufacturing Complete | 2018-09-10 13:05 | 2018-10-18 13:17 | 2018-11-30 10:55 | 2018-11-30 10:56
T19981 | Fourier Approach | 2019-01-24 | 232.2 | 182 | Gibson Maphosa | AB D2 | W1 | Issued for Manufacturing Start |  | 2018-10-18 13:17 | 2018-12-06 14:10 | [9 empty] | 2018-12-03 15:04: 2018-09-10 13:58
T19981 | Fourier Approach | 2019-01-24 | 2903.5 | 184 | Francois Burger | AB D1 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 | [7 empty] | 2018-09-10 14:25
T19981 | Fourier Approach | 2019-01-24 | 897.6 | 198 | Charlie Msiza | W2 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [10 empty] | 2018-12-03 15:04: 2018-09-12 08:14
T19981 | Fourier Approach | 2019-01-24 | 111.13 | 201 | Stephen Moshoeu | W1 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [10 empty] | 2018-12-03 15:03: 2018-09-12 08:34
T19981 | Fourier Approach | 2019-01-24 | 656.5 | 206 |  | B1 | Door | Installation Complete |  | 2018-10-18 13:17 |  |  |  |  | 2018-10-19 14:16 | 2018-10-19 14:18 |  |  |  |  | 2018-12-03 21:04: 2018-09-12 08:42 | 2018-10-19 14:18 | 2018-11-28 13:02 |  | 2018-10-19 09:25
T19981 | Fourier Approach | 2019-01-24 | 44.3 | 209 |  | W98 | Window | Cutting Aluminium Complete |  | 2018-10-18 13:17 |  |  | 2018-10-19 14:27 | 2018-12-06 15:04 |  | 2018-10-19 14:23 |  |  |  |  | 2018-10-19 08:59: 2018-10-19 09:06; 2018-12-03 15:03: 2018-09-13 13:03 | 2018-10-19 09:11 |  | 2018-10-19 09:06 |  | 2018-09-12 11:59
T19981 | Fourier Approach | 2019-01-24 | 999.9 | 210 | Alpheus Mjabulise Mziz | D3 | Door | Quality Control Start |  | 2018-10-18 13:17 | 2018-10-18 14:08 | 2018-10-18 14:08 | 2018-12-05 10:54 | 2018-12-05 12:58 | 2018-12-06 14:21 | 2018-12-06 14:21 | 2018-12-06 14:35 | 2019-01-08 15:31 | 2019-01-14 11:26 | 2019-01-14 12:34 | 2018-10-19 08:59: 2019-01-14 12:35 |  |  | 2018-09-12 12:00
T19981 | Fourier Approach | 2019-01-24 | 1212.1 | 211 | Phophi Raulinga | W56 | Window | Cancelled |  | 2018-10-18 13:17 | [10 empty] | 2018-12-03 21:04: 2018-09-12 12:05 |  |  |  |  | 2018-10-19 14:36
T19981 | Fourier Approach | 2019-01-24 | 123.4 | 214 | Tessah Ncube | D33 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 | [20 empty] | 2018-09-12 12:10
T19981 | Fourier Approach | 2019-01-24 | 4500.99 | 215 | Gibson Maphosa | DD01 | Clip44 | Handover to Factory Complete | 2018-09-12 23:33 | 2018-10-18 13:17
T19981 | Fourier Approach | 2019-01-24 | 1140.11 | 287 |  | FE-1198 | Window_123 | Handover to Factory Complete | 2019-01-07 11:29 | 2019-01-14 07:57
Q180822 | DuPlessis - Extras 2 | 2019-01-24 | 2100 | 290 |  | D08-1 | Vistafold | Handover to Factory Start | 2019-01-10 09:33
Q180822 | DuPlessis - Extras 2 | 2019-01-24 | 2100 | 291 |  | D08-2 | Vistafold | Handover to Factory Start | 2019-01-10 09:33
T-1189 | Test 1189 | 2019-01-25 | 150 | 288 | Charlie Msiza | W-100 | Window 100 | Snagging Complete | 2019-01-08 11:20 | 2019-01-08 11:21 | 2019-01-08 11:21 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:22 | 2019-01-08 11:23 | 2019-01-08 11:24 | 2019-01-08 11:25 | 2019-01-08 11:25 | 2019-01-08 11:25 | 2019-01-08 11:25 | 2019-01-08 11:25 | 2019-01-08 11:26 | 2019-01-08 11:26 | 2019-01-08 11:27 | 2019-01-08 11:33 | 2019-01-08 11:35
qwerty-01 | qwerty | 2019-01-25 | 6277.59 | 475 |  | D01 | Palace High Performance | Handover to Factory Start | 2019-01-14 09:47
qwerty-01 | qwerty | 2019-01-25 | 2257.57 | 476 |  | D01SL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:47
qwerty-01 | qwerty | 2019-01-25 | 3035.59 | 477 |  | D01SL44 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:47
qwerty-01 | qwerty | 2019-01-25 | 50 | 478 |  | D01SLL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:47
FP-001 | FourierProducts | 2019-01-25 | 0 | 405 |  | Cottg01-D02SL-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 406 |  | Cottg01-D02SL-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 6961.1 | 407 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 408 |  | Cottg01-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 6894.95 | 409 |  | Cottg01-D02Dr | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 5592.22 | 410 |  | Cottg01-D03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 411 |  | Cottg01-W01 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 2723.18 | 412 |  | Cottg01-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 413 |  | Cottg01-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 4360.36 | 414 |  | Cottg01-W03B | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 557.02 | 415 |  | Cottg01-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 536.54 | 416 |  | Cottg01-W05A | Crealco Swift 30.5 Window | Handover to Factory Complete | 2019-01-11 14:44 | 2019-01-14 07:56
FP-001 | FourierProducts | 2019-01-25 | 1094.18 | 417 |  | Cottg01-W05B | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 1099.07 | 418 |  | Cottg01-W05C | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 1037.28 | 419 |  | Cottg02-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 320.57 | 420 |  | Cottg02-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 3112.74 | 421 |  | Cottg02-D02 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 3061.26 | 422 |  | Cottg02-D02ins | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 2725.65 | 423 |  | Cottg02-W01 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 2763.45 | 424 |  | Cottg02-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 8512.66 | 425 |  | Cottg02-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 426 |  | Cottg02-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 1436.67 | 427 |  | Cottg02-W05 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 0 | 428 |  | Cottg02-W06 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 3450.81 | 429 |  | Cottg02-W07 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 1269.17 | 430 |  | Cottg02-W08 | 1000 Sliding Window | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 1063.9 | 431 |  | Cottg03-D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:44
FP-001 | FourierProducts | 2019-01-25 | 453.49 | 432 |  | Cottg03-D02 | Clip 44 Shop Front | Handover to Factory Complete | 2019-01-11 14:44 | 2019-01-14 09:13
e1 | Testing | 2019-01-25 | 100 | 451 |  | e1 | window 1 | Handover to Factory Start | 2019-01-14 09:26
e1 | Testing | 2019-01-25 | 100 | 452 |  | e2 | window 2 | Handover to Factory Start | 2019-01-14 09:26
e1 | Testing | 2019-01-25 | 200 | 453 |  | e3 | window 3 | Handover to Factory Start | 2019-01-14 09:26
e1 | Testing | 2019-01-25 | 300 | 454 |  | e4 | window 4 | Handover to Factory Start | 2019-01-14 09:26
e1 | Testing | 2019-01-25 | 400 | 455 |  | e5 | window 5 | Handover to Factory Start | 2019-01-14 09:26
testing | t1 | 2019-01-28 | 8500.09 | 433 |  | D02-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 8500.09 | 434 |  | D02-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 8500.09 | 435 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 7893.24 | 436 |  | D03-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 7893.24 | 437 |  | D03-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 6767.26 | 438 |  | D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 6322.78 | 439 |  | D01-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
testing | t1 | 2019-01-28 | 6322.78 | 440 |  | D01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-11 14:47
qwerty-02 | qwerty02 | 2019-01-31 | 6961.1 | 479 |  | Cottg01-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 6894.95 | 480 |  | Cottg01-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 5592.22 | 481 |  | Cottg01-D02Dr | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 2723.18 | 482 |  | Cottg01-D02SL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 4360.36 | 483 |  | Cottg01-D03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 557.02 | 484 |  | Cottg01-W01 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 536.54 | 485 |  | Cottg01-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1094.18 | 486 |  | Cottg01-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1099.07 | 487 |  | Cottg01-W03B | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1037.28 | 488 |  | Cottg01-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 320.57 | 489 |  | Cottg01-W05A | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3112.74 | 490 |  | Cottg01-W05B | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3061.26 | 491 |  | Cottg01-W05C | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 2725.65 | 492 |  | Cottg02-D01L | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 2763.45 | 493 |  | Cottg02-D01R | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 8512.66 | 494 |  | Cottg02-D02 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1436.67 | 495 |  | Cottg02-D02ins | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3450.81 | 496 |  | Cottg02-W01 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1269.17 | 497 |  | Cottg02-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1063.9 | 498 |  | Cottg02-W03 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 453.49 | 499 |  | Cottg02-W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3504.97 | 500 |  | Cottg02-W05 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3339.63 | 501 |  | Cottg02-W06 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3025.7 | 502 |  | Cottg02-W07 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 3025.7 | 503 |  | Cottg02-W08 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 2776.73 | 504 |  | Cottg03-D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 6478.72 | 505 |  | Cottg03-D02 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 1137.66 | 506 |  | Cottg03-D02Ins | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 636.66 | 507 |  | Cottg03-W01 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 640.6 | 508 |  | Cottg03-W02 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 09:48
qwerty-02 | qwerty02 | 2019-01-31 | 4680.99 | 509 |  | Main-W01 | 1000 Sliding Window | Handover to Factory Start | 2019-01-14 09:48
mrt-1 | matching refs test | 2019-02-01 | 8500.09 | 510 |  | D02_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 8500.09 | 511 |  | D02_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 8500.09 | 512 |  | D02_3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 7893.24 | 513 |  | D03_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 7893.24 | 514 |  | D03_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 6767.26 | 515 |  | D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 6322.78 | 516 |  | D01-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 6322.78 | 517 |  | D01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 8403.81 | 518 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 19088.95 | 519 |  | D04 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 3425.11 | 520 |  | D04TL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 12498.14 | 521 |  | DW01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 12508.79 | 522 |  | DW01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 12512.92 | 523 |  | DW01-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 4316.25 | 524 |  | W01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 4226.97 | 525 |  | W01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 2950.77 | 526 |  | W03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 2939.15 | 527 |  | W03-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 4167.29 | 528 |  | W03-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 3519.01 | 529 |  | W07 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 2524.44 | 530 |  | W10 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 2382.04 | 531 |  | W10-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 09:53
mrt-1 | matching refs test | 2019-02-01 | 1638.85 | 532 |  | W11 | Crealco Icon Patio Door | Handover to Factory Start | 2019-01-14 09:53
Q1234 | Koning test | 2019-02-02 | 9241.98 | 299 |  | D03-1 | Clip 44 | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 9241.98 | 300 |  | D03-2 | Clip 44 | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 5302.3 | 301 |  | D04-1 | Clip 44 | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 5302.3 | 302 |  | D04-2 | Clip 44 | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 12427.93 | 303 |  | SFD01-1 | Vistafold | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 12427.93 | 304 |  | SFD01-2 | Vistafold | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 1203.01 | 305 |  | SFD01 -1 | Swift 30.5 Window | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 1203.01 | 306 |  | SFD01 -2 | Swift 30.5 Window | Handover to Factory Start | 2019-01-10 15:14
Q1234 | Koning test | 2019-02-02 | 12427.92 | 307 |  | SFD02 | Vistafold | Handover to Factory Start | 2019-01-10 15:14
Q12345 | Koning test 2 | 2019-02-02 | 9241.98 | 316 |  | D03-1 | Clip 44 Shopfront | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 9241.98 | 317 |  | D03-2 | Clip 44 Shopfront | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 5302.3 | 318 |  | D04-1 | Clip 44 Shopfront | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 5302.3 | 319 |  | D04-2 | Clip 44 Shopfront | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 12427.93 | 320 |  | SFD01-1 | Vistafold | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 12427.93 | 321 |  | SFD01-2 | Vistafold | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 1203.01 | 322 |  | SFD01 -1 | Swift 30.5 Window | Handover to Factory Start | 2019-01-10 15:41
Q12345 | Koning test 2 | 2019-02-02 | 1203.01 | 323 |  | SFD01 -2 | Swift 30.5 Window | Handover to Factory Start | 2019-01-10 15:42
Q12345 | Koning test 2 | 2019-02-02 | 12427.93 | 324 |  | SFD02 | Vistafold | Handover to Factory Start | 2019-01-10 15:42
Q54321 | Jan | 2019-02-13 | 8500.09 | 533 |  | D02_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 8500.09 | 534 |  | D02_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 8500.09 | 535 |  | D02_3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 7893.24 | 536 |  | D03_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 7893.24 | 537 |  | D03_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 6767.26 | 538 |  | D01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 6322.78 | 539 |  | D01-1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 6322.78 | 540 |  | D01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 8403.81 | 541 |  | D02-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 19088.95 | 542 |  | D04 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 3425.11 | 543 |  | D04TL | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 12498.14 | 544 |  | DW01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 12508.79 | 545 |  | DW01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 12512.92 | 546 |  | DW01-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 4316.25 | 547 |  | W01 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 4226.97 | 548 |  | W01-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 2950.77 | 549 |  | W03 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 2939.15 | 550 |  | W03-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 4167.29 | 551 |  | W03-3 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 3519.01 | 552 |  | W07 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 2524.44 | 553 |  | W10 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 2382.04 | 554 |  | W10-2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 10:04
Q54321 | Jan | 2019-02-13 | 1638.85 | 555 |  | W11 | Crealco Icon Patio Door | Handover to Factory Start | 2019-01-14 10:04
Q654321 | nel | 2019-03-30 | 1172.94 | 556 |  | W01_1 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1172.94 | 557 |  | W01_2 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1172.94 | 558 |  | W01_3 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1172.94 | 559 |  | W01_4 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 846.75 | 560 |  | W05_1 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 846.75 | 561 |  | W05_2 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 943.25 | 562 |  | W09_1 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 943.25 | 563 |  | W09_2 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 785.58 | 564 |  | W12_1 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 785.58 | 565 |  | W12_2 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 2578.23 | 566 |  | W02 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 6176.6 | 567 |  | W03 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1159.26 | 568 |  | W04 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1106.25 | 569 |  | W06 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1388.34 | 570 |  | W07 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 797.06 | 571 |  | W08 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 1614.43 | 572 |  | W10 | Crealco Icon Patio Door | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 481.31 | 573 |  | W11 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 598.84 | 574 |  | W13 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:10
Q654321 | nel | 2019-03-30 | 277.46 | 575 |  | W14 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:10
Q7654321 | Pieters | 2019-05-05 | 9241.98 | 578 |  | D03_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 9241.98 | 579 |  | D03_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 5302.3 | 580 |  | D04_1 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 5302.3 | 581 |  | D04_2 | Clip 44 Shop Front | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 12427.93 | 582 |  | SFD01_1 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 12427.93 | 583 |  | SFD01_2 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 1203.01 | 584 |  | SFD01 SidelIght_1 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 1203.01 | 585 |  | SFD01 SidelIght_2 | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 12427.92 | 586 |  | SFD02 | Vistafold Sliding Folding Door | Handover to Factory Start | 2019-01-14 12:17
Q7654321 | Pieters | 2019-05-05 | 1245.76 | 587 |  | SFD02-sidelight | Crealco Swift 30.5 Window | Handover to Factory Start | 2019-01-14 12:17