## Filters
ContractReference | Description | DueDate | Value | ContractItemId | UserName | LineReferenceNumber | AluminiumSystem | Status | Handover to Factory Start | Handover to Factory Complete | Issued for Manufacturing Start | Issued for Manufacturing Complete | Cutting Aluminium Start | Cutting Aluminium Complete | Machining Start | Machining Complete | Assembly Start | Assembly Complete | Glazing Start | Glazing Complete | Quality Control Start | Quality Control Complete | Wrapping and Despatching Start | Wrapping and Despatching Complete | Deliverey Start | Deliverey Complete | Installation Start | Installation Complete | Snagging Start | Snagging Complete | Cancelled
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 141 | Reginald Nemalili | W11-1 | Cas30.5-1 | Wrapping and Despatching Complete | 2018-08-13 20:29 | [13 empty] | 2018-08-13 20:40 | 2018-08-27 11:55
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 141 | Reginald Nemalili | W11-1 | Cas30.5-1 | Wrapping and Despatching Complete | 2018-08-13 20:29 | [13 empty] | 2018-08-13 20:40 | 2018-08-27 11:55
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 142 |  | W11-2 | Cas30.5-2 | Machining Complete | 2018-08-13 20:29 | [6 empty] | 2018-08-29 19:33
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 143 |  | W11-3 | Cas30.5-3 | Deliverey Start | 2018-08-13 20:29 | [15 empty] | 2018-08-13 20:40
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 144 |  | W11-4 | Cas30.5-4 | Deliverey Complete | 2018-08-13 20:29 | [15 empty] | 2018-08-13 20:41 | 2018-09-06 08:24
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 145 | Reginald Nemalili | W11-5 | Cas30.5-5 | Assembly Complete | 2018-08-13 20:29 | [6 empty] | 2018-08-13 21:01 | 2018-08-13 21:16 | 2018-08-13 21:18 | [6 empty] | 2018-08-13 20:41
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 146 |  | W01 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 147 |  | W02 | Cas30.5 | Quality Control Start | 2018-08-13 20:29 |  |  |  |  | 2018-08-29 19:35 | [6 empty] | 2018-08-29 19:36
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 148 |  | W03 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-08-13 21:13
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 149 |  | W04 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-08-13 21:13
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 150 |  | W05 | Cas30.5 | Glazing Complete | 2018-08-13 20:29 | [9 empty] | 2018-08-27 11:49 | 2018-08-27 11:49
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 151 |  | W06 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 152 |  | W07 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 153 |  | W08 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 154 |  | W09 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 155 |  | W10 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 156 |  | W12 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 157 |  | W13 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 5000 | 158 |  | SFD01 | Vistafold | Handover to Factory Start | 2018-08-13 20:29
Q18082501 | DuPlessis | 2018-08-16 | 7000 | 159 |  | SFD02 | Vistafold | Deliverey Start | 2018-08-13 20:29 | [15 empty] | 2018-08-13 20:42
Q18081565 | Malvin Mashaba | 2018-08-31 | 3285 | 171 | Steph Ngubeni | D01 | Clip 44 Single Hinged Door | Issued for Manufacturing Start |  |  | 2018-09-06 08:24
Q18082301B | DuPlessis - Extras | 2018-09-02 | 1195 | 160 |  | WA-1 | Crealco Swift 30.5 Window -1 | Glazing Complete | 2018-08-13 20:53 | [10 empty] | 2018-08-13 22:17
Q18082301B | DuPlessis - Extras | 2018-09-02 | 1195 | 161 |  | WA-2 | Crealco Swift 30.5 Window -2 | Glazing Complete | 2018-08-13 20:53 | [10 empty] | 2018-08-27 11:48 | 2018-08-27 11:48
Q18082301B | DuPlessis - Extras | 2018-09-02 | 1195 | 162 | Reginald Nemalili | WA-3 | Crealco Swift 30.5 Window -3 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-08-29 19:34
Q18082301B | DuPlessis - Extras | 2018-09-02 | 484 | 163 |  | WB-1 | Crealco Swift 30.5 Window -1 | Handover to Factory Start | 2018-08-13 20:53
Q18082301B | DuPlessis - Extras | 2018-09-02 | 484 | 164 |  | WB-2 | Crealco Swift 30.5 Window -2 | Assembly Complete | 2018-08-13 20:53 | [8 empty] | 2018-08-15 08:31
Q18082301B | DuPlessis - Extras | 2018-09-02 | 484 | 165 |  | WB-3 | Crealco Swift 30.5 Window -3 | Handover to Factory Start | 2018-08-13 20:53
Q18082301B | DuPlessis - Extras | 2018-09-02 | 742 | 166 |  | WC | Crealco Swift 30.5 Window | Handover to Factory Start | 2018-08-13 20:53
Q18082301B | DuPlessis - Extras | 2018-09-02 | 789 | 167 | Alpheus Mjabulise Mzizi | WG-2 | Crealco Swift 30.5 window | Handover to Factory Start | 2018-08-15 09:24
C201807-test 01 | Test q1 | 2018-10-13 | 1290 | 169 | Charlie Msiza | A18 | Window 2100 | Handover to Factory Start | 2018-08-23 21:06
C201807-test 01 | Test q1 | 2018-10-13 | 1290 | 170 | Alpheus Mjabulise Mzizi | A19 | Window 2101 | Handover to Factory Start | 2018-08-23 21:08
C201807-test 01 | Test q1 | 2018-10-13 | 400.5 | 172 | Charlie Msiza | A100 | Window 100 | Handover to Factory Start | 2018-09-06 09:25
C201807-test 01 | Test q1 | 2018-10-13 | 500 | 132 |  | A2-1 | Win 29-1 | Glazing Complete | 2018-08-13 09:03 | [10 empty] | 2018-08-13 21:11
C201807-test 01 | Test q1 | 2018-10-13 | 500 | 133 |  | A2-2 | Win 29-2 | Handover to Factory Complete | 2018-08-13 09:03 | 2018-09-06 08:24
C201807-test 01 | Test q1 | 2018-10-13 | 500 | 134 |  | A2-3 | Win 29-3 | Handover to Factory Start | 2018-08-13 09:03
C201807-test 01 | Test q1 | 2018-10-13 | 500 | 135 |  | A2-4 | Win 29-4 | Issued for Manufacturing Start | 2018-08-13 09:03 |  | 2018-08-13 09:13
C201807-test 01 | Test q1 | 2018-10-13 | 500 | 136 |  | A2-5 | Win 29-5 | Issued for Manufacturing Complete | 2018-08-13 09:03 |  | 2018-08-13 09:12 | 2018-08-13 09:27 | 2018-08-13 09:13
C201807-test 01 | Test q1 | 2018-10-13 | 230 | 137 |  | B1-1 | Dr 10-1 | Handover to Factory Start | 2018-08-13 09:03
C201807-test 01 | Test q1 | 2018-10-13 | 230 | 138 |  | B1-2 | Dr 10-2 | Handover to Factory Start | 2018-08-13 09:03
C201807-test 01 | Test q1 | 2018-10-13 | 200 | 139 |  | A1 | Win 10 | Handover to Factory Start | 2018-08-13 09:03
C201807-test 01 | Test q1 | 2018-10-13 | 1125 | 140 |  | W01-1 | Cas30.5 | Machining Complete | 2018-08-13 20:05 |  |  |  | 2018-08-15 08:35 |  |  | 2018-08-15 08:35