## Filters
ContractReference | Description | DueDate | Value | ContractItemId | UserName | LineReferenceNumber | AluminiumSystem | Status | Handover to Factory Start | Handover to Factory Complete | Issued for Manufacturing Start | Issued for Manufacturing Complete | Cutting Aluminium Start | Cutting Aluminium Complete | Machining Start | Machining Complete | Assembly Start | Assembly Complete | Glazing Start | Glazing Complete | Quality Control Start | Quality Control Complete | Wrapping and Despatching Start | Wrapping and Despatching Complete | Delivery Start | Delivery Complete | Installation Start | Installation Complete | Snagging Start | Snagging Complete | Cancelled
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 141 | Reginald Nemalili | W11-1 | Cas30.5-1 | Snagging Start | 2018-08-13 20:29 | 2018-09-14 12:43 | 2018-10-19 09:28 | 2018-10-19 14:14 | 2018-11-22 11:38 | 2018-11-22 11:38 | 2018-09-14 13:02 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-21 14:11 | 2018-11-22 11:40 | 2018-09-13 00:02 | 2018-10-30 12:25 | 2018-08-13 20:40 | 2018-08-27 11:55 | 2018-09-06 12:39 | 2018-11-22 11:42 | 2018-11-22 11:43 | 2018-11-22 11:43 | 2018-09-13 13:08 | 2018-11-22 11:37 | 2018-09-14 12:34
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 141 | Reginald Nemalili | W11-1 | Cas30.5-1 | Snagging Start | 2018-08-13 20:29 | 2018-09-14 12:43 | 2018-10-19 09:28 | 2018-10-19 14:14 | 2018-11-22 11:38 | 2018-11-22 11:38 | 2018-09-14 13:02 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-22 11:39 | 2018-11-21 14:11 | 2018-11-22 11:40 | 2018-09-13 00:02 | 2018-10-30 12:25 | 2018-08-13 20:40 | 2018-08-27 11:55 | 2018-09-06 12:39 | 2018-11-22 11:42 | 2018-11-22 11:43 | 2018-11-22 11:43 | 2018-09-13 13:08 | 2018-11-22 11:37 | 2018-09-14 12:34
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 142 |  | W11-2 | Cas30.5-2 | Wrapping and Despatching Complete | 2018-08-13 20:29 | 2018-10-30 09:24 | 2018-11-21 14:29 |  | 2018-09-14 12:44 |  | 2018-11-21 14:29 | 2018-08-29 19:33 | 2018-11-21 14:29 | 2018-09-12 16:00 | 2018-10-19 08:58 | 2018-10-19 09:27 | 2018-11-21 14:29 |  | 2018-11-21 14:30 | 2018-11-26 10:44 | 2018-10-30 12:26 | 2018-10-30 13:04 | 2018-11-21 14:29 |  |  |  | 2018-09-13 13:08
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 143 |  | W11-3 | Cas30.5-3 | Delivery Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [8 empty] | 2018-10-18 13:22 | 2018-10-30 12:44 |  |  |  |  | 2018-09-13 13:09 | 2018-11-28 11:00 |  | 2018-09-13 00:03
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 144 |  | W11-4 | Cas30.5-4 | Wrapping and Despatching Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [6 empty] | 2018-09-13 12:53 | 2018-10-18 13:12 |  |  |  |  | 2018-11-26 11:31 |  | 2018-08-13 20:41 | 2018-09-06 08:24 |  |  |  |  | 2018-11-22 13:26
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 145 | Reginald Nemalili | W11-5 | Cas30.5-5 | Delivery Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [5 empty] | 2018-08-13 21:01 | 2018-08-13 21:16 | 2018-08-13 21:18 |  |  | 2018-10-19 08:59 | 2018-11-28 10:54 | 2018-12-03 15:03 | 2018-12-03 15:04 | 2018-12-03 21:04
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 146 |  | W01 | Cas30.5 | Snagging Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [11 empty] | 2018-09-12 22:57 | [6 empty] | 2018-11-21 14:32 | 2018-11-29 15:04
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 147 |  | W02 | Cas30.5 | Cutting Aluminium Complete | 2018-08-13 20:29 | 2018-10-18 13:17 |  |  | 2018-11-21 14:40 | 2018-11-30 10:55 |  |  | 2018-10-30 12:17 | 2018-11-21 14:30 |  |  | 2018-08-29 19:36
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 148 |  | W03 | Cas30.5 | Handover to Factory Start | 2018-08-13 20:29 | 2018-08-13 21:13 | [13 empty] | 2018-09-12 16:01
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 149 |  | W04 | Cas30.5 | Delivery Complete | 2018-08-13 20:29 | 2018-08-13 21:13 | [8 empty] | 2018-11-21 14:41 | 2018-11-21 14:42 |  |  |  |  | 2018-11-26 11:18 | 2018-12-03 21:04
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 150 |  | W05 | Cas30.5 | Snagging Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [8 empty] | 2018-08-27 11:49 | 2018-08-27 11:49 | [8 empty] | 2018-10-19 09:00
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 151 |  | W06 | Cas30.5 | Delivery Start | 2018-08-13 20:29 | 2018-10-18 13:17 | [14 empty] | 2018-10-19 14:20
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 152 |  | W07 | Cas30.5 | Issued for Manufacturing Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | 2018-11-29 15:05 | 2018-11-29 15:05
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 153 |  | W08 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17 |  | 2018-09-10 15:13
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 154 |  | W09 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 155 |  | W10 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 156 |  | W12 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17
Q18082501 | DuPlessis | 2018-08-16 | 1400 | 157 |  | W13 | Cas30.5 | Issued for Manufacturing Start | 2018-08-13 20:29 | 2018-10-18 13:17 | 2018-09-13 12:55 | [19 empty] | 2018-11-29 15:06
Q18082501 | DuPlessis | 2018-08-16 | 5000 | 158 |  | SFD01 | Vistafold | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17 |  |  |  |  | 2018-09-13 00:04
Q18082501 | DuPlessis | 2018-08-16 | 7000 | 159 |  | SFD02 | Vistafold | Handover to Factory Complete | 2018-08-13 20:29 | 2018-10-18 13:17 | [14 empty] | 2018-08-13 20:42
Q18081565 | Malvin Mashaba | 2018-08-31 | 3285 | 171 |  | D01 | Clip 44 Single Hinged Door | Machining Complete |  | 2018-10-18 13:17 | 2018-09-06 08:24 |  |  |  |  | 2018-10-30 09:34 |  |  |  | 2018-09-13 12:55 |  |  |  |  | 2018-10-19 14:33
C201807-01test | test 123 | 2018-10-13 | 3489.21 | 176 |  | AB D1-1 | Door | Handover to Factory Complete | 2018-09-10 12:33 | 2018-10-18 13:17
C201807-01test | test 123 | 2018-10-13 | 3489.21 | 177 |  | AB D1-2 | Door | Handover to Factory Complete | 2018-09-10 12:33 | 2018-10-18 13:17
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 2589 | 216 | Charlie Msiza | W01 | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-22 15:53 | 2018-11-27 08:34
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1976 | 217 | Patric Kola | W02A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:34
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1976 | 218 | ShaSha Raulinga | W02B | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-27 07:37 | 2018-12-03 00:15
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 219 | Patric Kola | W03A | CASEMENT 30.5 WINDOW | Handover to Factory Complete | 2018-11-27 07:38 | 2018-12-03 00:15
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 220 | Patric Kola | W03B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:39
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 221 | Charlie Msiza | W03C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:48
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 222 | Charlie Msiza | W03D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:50
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 223 | Charlie Msiza | W03E | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:51
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1710 | 224 | Steph Ngubeni | W04A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:53
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1710 | 225 | Obed M Tlale | W04B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:54
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1060 | 226 | Obed M Tlale | W05A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:55
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1444 | 227 | Obed M Tlale | W05B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:56
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1060 | 228 | Obed M Tlale | W05 LAM | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 07:58
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1444 | 229 | ShaSha Raulinga | W05 TSG OBS | CASEMENT 30.5 WINDOW | Handover to Factory Complete |  | 2018-11-27 07:59
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 961 | 230 | ShaSha Raulinga | W06 | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:00
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 231 | ShaSha Raulinga | W07A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:01
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 232 | ShaSha Raulinga | W07B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:02
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 233 | Obed M Tlale | W07C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:04
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 644 | 234 | Steph Ngubeni | W07D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:06
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 235 | Steph Ngubeni | W07 TSG OBS A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:07
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 236 | Steph Ngubeni | W07 TSG OBS B | CASEMENT 30.5 WINDOW | Handover to Factory Complete |  | 2018-11-27 08:08
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 237 | Obed M Tlale | W07 TSG OBS C | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:09
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 238 | Obed M Tlale | W07 TSG OBS D | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:10
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 239 | Obed M Tlale | W07 TSG OBS E | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:11
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 240 | Obed M Tlale | W07 TSG OBS F | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:12
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1246 | 241 | Charlie Msiza | W09A | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:13
PN111297 | K.S.W.(LAMDEN) | 2018-11-22 | 1274 | 242 | Charlie Msiza | W09B | CASEMENT 30.5 WINDOW | Handover to Factory Start | 2018-11-27 08:13
Q18091932 | Nick Artisans | 2018-12-05 | 10898.59 | 263 |  | D01 | WPalaceM | Assembly Start | 2018-11-30 09:15 | 2018-11-30 09:22 | [6 empty] | 2018-11-30 09:22
Q18082301B | DuPlessis - Extras | 2018-12-06 | 444.4 | 207 | Lucky Nekhudzhiga | W4 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [18 empty] | 2018-09-12 08:46
Q18082301B | DuPlessis - Extras | 2018-12-06 | 555.5 | 208 |  | WS-2 | window | Cancelled |  | 2018-10-18 13:17 | [17 empty] | 2018-09-12 08:48 |  |  | 2018-10-19 14:31
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 160 |  | WA-1 | Crealco Swift 30.5 Window -1 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [7 empty] | 2018-09-10 15:12 |  | 2018-08-13 22:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 161 |  | WA-2 | Crealco Swift 30.5 Window -2 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [9 empty] | 2018-08-27 11:48 | 2018-08-27 11:48
Q18082301B | DuPlessis - Extras | 2018-12-06 | 1195 | 162 | Reginald Nemalili | WA-3 | Crealco Swift 30.5 Window -3 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 163 |  | WB-1 | Crealco Swift 30.5 Window -1 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 164 |  | WB-2 | Crealco Swift 30.5 Window -2 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17 | [7 empty] | 2018-08-15 08:31
Q18082301B | DuPlessis - Extras | 2018-12-06 | 484 | 165 |  | WB-3 | Crealco Swift 30.5 Window -3 | Handover to Factory Complete | 2018-08-13 20:53 | 2018-10-18 13:17
Q18082301B | DuPlessis - Extras | 2018-12-06 | 742 | 166 |  | WC | Crealco Swift 30.5 Window | Cutting Aluminium Start | 2018-08-13 20:53 | 2018-10-18 13:17 |  |  | 2018-10-19 14:27
Q18082301B | DuPlessis - Extras | 2018-12-06 | 789 | 167 | Alpheus Mjabulise Mzizi | WG-2 | Crealco Swift 30.5 window | Issued for Manufacturing Start | 2018-08-15 09:24 | 2018-10-18 13:17 | 2018-12-05 09:52 |  |  | 2018-09-13 12:52
Q18100751 | Alves | 2018-12-07 | 6515 | 265 | Reymond Moshoeu | W30 | Side hung | Wrapping and Despatching Start | [5 empty] | 2018-11-30 11:04 | 2018-12-03 00:16 | 2018-12-03 09:12 | 2018-12-03 21:05 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-03 21:06 | 2018-12-04 12:56 | 2018-12-05 08:58
Q18100751 | Alves | 2018-12-07 | 5131 | 266 | Reymond Moshoeu | W27 | Side hung | Machining Start | [5 empty] | 2018-11-30 11:12 | 2018-12-03 09:25
Don | Office | 2018-12-11 | 2689 | 264 | Reymond Moshoeu | D01 | Prima PD | Machining Complete |  |  |  |  | 2018-11-30 10:46 | 2018-11-30 10:56 | 2018-11-30 11:52 | 2018-11-30 13:18
C201807-02 | Fourier Approach | 2018-12-12 | 897.6 | 198 | Charlie Msiza | W2 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [13 empty] | 2018-09-12 08:14
C201807-02 | Fourier Approach | 2018-12-12 | 111.13 | 201 | Stephen Moshoeu | W1 | Window | Handover to Factory Complete |  | 2018-10-18 13:17 | [12 empty] | 2018-09-12 08:34
C201807-02 | Fourier Approach | 2018-12-12 | 656.5 | 206 |  | B1 | Door | Installation Complete |  | 2018-10-18 13:17 |  |  |  |  | 2018-10-19 14:16 | 2018-10-19 14:18 | [8 empty] | 2018-09-12 08:42 |  | 2018-10-19 14:18 | 2018-11-28 13:02 |  | 2018-10-19 09:25
C201807-02 | Fourier Approach | 2018-12-12 | 2213.6 | 180 |  | AB D1-1 | W1 | Handover to Factory Complete | 2018-09-10 13:05 | 2018-10-18 13:17
C201807-02 | Fourier Approach | 2018-12-12 | 2213.6 | 181 |  | AB D1-2 | W1 | Issued for Manufacturing Complete | 2018-09-10 13:05 | 2018-10-18 13:17 | 2018-11-30 10:55 | 2018-11-30 10:56
C201807-02 | Fourier Approach | 2018-12-12 | 232.2 | 182 | Gibson Maphosa | AB D2 | W1 | Handover to Factory Complete |  | 2018-10-18 13:17 | [13 empty] | 2018-09-10 13:58
C201807-02 | Fourier Approach | 2018-12-12 | 2903.5 | 184 | Francois Burger | AB D1 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 | [7 empty] | 2018-09-10 14:25
C201807-02 | Fourier Approach | 2018-12-12 | 44.3 | 209 |  | W98 | Window | Cutting Aluminium Start |  | 2018-10-18 13:17 |  |  | 2018-10-19 14:27 |  |  | 2018-10-19 14:23 |  |  |  |  | 2018-10-19 09:06 |  | 2018-09-13 13:03 |  |  |  | 2018-10-19 09:11 |  | 2018-10-19 09:06 |  | 2018-09-12 11:59
C201807-02 | Fourier Approach | 2018-12-12 | 999.9 | 210 | Alpheus Mjabulise Mzizi | D3 | Door | Cutting Aluminium Complete |  | 2018-10-18 13:17 | 2018-10-18 14:08 | 2018-10-18 14:08 | 2018-12-05 10:54 | 2018-12-05 12:58 | [14 empty] | 2018-09-12 12:00
C201807-02 | Fourier Approach | 2018-12-12 | 1212.1 | 211 | Phophi Raulinga | W56 | Window | Cancelled |  | 2018-10-18 13:17 | [14 empty] | 2018-09-12 12:05 | [5 empty] | 2018-10-19 14:36
C201807-02 | Fourier Approach | 2018-12-12 | 123.4 | 214 | Tessah Ncube | D33 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 | [20 empty] | 2018-09-12 12:10
C201807-02 | Fourier Approach | 2018-12-12 | 4500.99 | 215 | Gibson Maphosa | DD01 | Clip44 | Handover to Factory Complete | 2018-09-12 23:33 | 2018-10-18 13:17
Q18060734 | Peace Msinde | 2018-12-12 | 8992 | 267 | Obed M Tlale | D01 | WClip44 | Assembly Complete | [8 empty] | 2018-12-04 14:41 | 2018-12-04 15:34
Q18060734 | Peace Msinde | 2018-12-12 | 7962 | 268 | Daniel Kanyane (Daniels) | SD06 | WClip44 | Assembly Start | [8 empty] | 2018-12-04 14:41
Q18060734 | Peace Msinde | 2018-12-12 | 9955 | 271 | Patric Kola | D02 | WVista | Assembly Start | [8 empty] | 2018-12-04 15:11 | 2018-12-04 15:31
C201807-02 | Fourier Approach | 2018-12-12 | 150.5 | 275 | Cynthia Ngcobo | W0119 | Window | Handover to Factory Start | 2018-12-05 08:45
C201807-02 | Fourier Approach | 2018-12-12 | 200.3 | 276 | Francois Burger | D1441 | Door | Handover to Factory Start | 2018-12-05 08:51
C201807-test 01 | Test q1 | 2018-12-20 | 1290 | 169 | Charlie Msiza | A18 | Window 2100 | Cutting Aluminium Start | 2018-08-23 21:06 | 2018-10-18 13:17 |  |  | 2018-10-19 09:13
C201807-test 01 | Test q1 | 2018-12-20 | 1290 | 170 | Alpheus Mjabulise Mzizi | A19 | Window 2101 | Handover to Factory Complete | 2018-08-23 21:08 | 2018-09-17 21:02
C201807-test 01 | Test q1 | 2018-12-20 | 123.63 | 175 | Patric Kola | AB D1 | Door | Handover to Factory Complete |  | 2018-10-18 13:17 |  |  |  |  | 2018-09-10 12:28
C201807-test 01 | Test q1 | 2018-12-20 | 500 | 132 |  | A2-1 | Win 29-1 | Wrapping and Despatching Start | 2018-08-13 09:03 | 2018-10-18 13:17 | [9 empty] | 2018-08-13 21:11 | 2018-09-06 10:54 |  | 2018-11-21 14:31
C201807-test 01 | Test q1 | 2018-12-20 | 500 | 133 |  | A2-2 | Win 29-2 | Glazing Start | 2018-08-13 09:03 | 2018-10-18 13:17 | [8 empty] | 2018-10-30 12:29 |  | 2018-09-14 13:31
C201807-test 01 | Test q1 | 2018-12-20 | 500 | 134 |  | A2-3 | Win 29-3 | Installation Start | 2018-08-13 09:03 | 2018-09-17 20:50 | [16 empty] | 2018-10-19 09:05
C201807-test 01 | Test q1 | 2018-12-20 | 500 | 135 |  | A2-4 | Win 29-4 | Issued for Manufacturing Start | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-08-13 09:13 | 2018-09-17 20:50
C201807-test 01 | Test q1 | 2018-12-20 | 500 | 136 |  | A2-5 | Win 29-5 | Handover to Factory Complete | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-08-13 09:12 | 2018-08-13 09:27 | 2018-08-13 09:13
C201807-test 01 | Test q1 | 2018-12-20 | 230 | 137 |  | B1-1 | Dr 10-1 | Handover to Factory Complete | 2018-08-13 09:03 | 2018-10-18 13:17
C201807-test 01 | Test q1 | 2018-12-20 | 230 | 138 |  | B1-2 | Dr 10-2 | Handover to Factory Complete | 2018-08-13 09:03 | 2018-10-18 13:17
C201807-test 01 | Test q1 | 2018-12-20 | 200 | 139 |  | A1 | Win 10 | Handover to Factory Complete | 2018-08-13 09:03 | 2018-10-18 13:17 | 2018-09-06 12:16 |  |  |  | 2018-09-06 12:16 | 2018-09-06 12:26 | [8 empty] | 2018-09-06 12:26 | 2018-09-06 12:30
C201807-test 01 | Test q1 | 2018-12-20 | 400.5 | 172 | Charlie Msiza | A100 | Window 100 | Installation Start | 2018-09-06 09:25 | 2018-10-18 13:17 | [16 empty] | 2018-10-19 14:13
C201807-test 01 | Test q1 | 2018-12-20 | 1125 | 140 |  | W01-1 | Cas30.5 | Handover to Factory Complete | 2018-08-13 20:05 | 2018-10-18 13:17 |  |  | 2018-08-15 08:35 |  |  | 2018-08-15 08:35
Q18111303B | Koning | 2018-12-21 | 1945 | 246 |  | W01-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1945 | 247 |  | W01-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1802 | 248 |  | W05-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1802 | 249 |  | W05-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 438 | 260 |  | W04 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 605 | 261 |  | W10 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 829 | 262 |  | W11 | Swift 30.5 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1676 | 250 |  | W06-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1676 | 251 |  | W06-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1500 | 252 |  | W07-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1500 | 253 |  | W07-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1962 | 254 |  | W08-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1962 | 255 |  | W08-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 2879 | 256 |  | W09-1 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 2879 | 257 |  | W09-2 | WSS1000 | Handover to Factory Start | 2018-11-30 08:53
Q18111303B | Koning | 2018-12-21 | 1298 | 258 |  | W02 | Swift 30.5 | Handover to Factory Complete | 2018-11-30 08:53 | 2018-11-30 10:57
Q18111303B | Koning | 2018-12-21 | 1082 | 259 |  | W03 | Swift 30.5 | Handover to Factory Complete | 2018-11-30 08:53 | 2018-12-03 00:23